Supplementary Information for

Making Sense of Hospital Project (Mis)Performance: Over Budget, Late, Time and Time Again—Why? And What Can Be Done About It?

Peter E.D. Love a, Lavagnon A. Ika b

a School of Civil and Mechanical Engineering, Curtin University, Perth, WA 6845, Australia

b Telfer School of Management, University of Ottawa, Ottawa, ON KIN 6N5, Canada

Table S1

Examples of hospitals experiencing budget increases, delays and poor quality

| Hospital | Location | Details | Comments | Source |
| --- | --- | --- | --- | --- |
| Libya Medical Center, Tripoli | Libya | Original budget: 31 million GBP Revised cost: 156 million GBP The project was planned to be completed in August 1984, but its numerous difficulties led to several extensions, and the project was finally completed in August 1996, 12 years and 7 months late. | In November 1973, a contract for 31 million GBP was signed for the building works. The cabinet approved an increase of this to 45 million GBP in October 1975. Then, in July 1977, construction work was suspended. In August 1981, the second contract of 78 million GBP was signed for the completion stage. Technical and planning problems arose throughout the design and build. Following completion in August 1996, the final account for the second stage contract (settled in December 1999) showed that the cost had increased to 156 million GBP. Changing scope had led to preparing a new design and redesigning existing architecture plans. The project was plagued with delays in procuring equipment. | [1] |
| Guy’s Hospital Phase III Development, London | UK | Original budget: 83.1 million GBP Revised cost: 151.8 million GBP, plus 8.1 million GBP for modifications required to reflect changes in its use. The project was completed in April 1997, 3 years and 4 months late. | The Treasury approved the project in 1986 with an initial estimate of 35 million GBP, which was revised to 74.6 million GBP in 1989, with 8.5 million GBP for site location factors (83.1 million GBP). In 1986, the project was planned to be completed in December 1993. However, it was beset by difficulties that led to several extensions to the project completion date despite adopting various strategies to maintain the program. As a result, the project was finally completed in April 1997. The new building was opened to patients in July 1997. The reasons for the subsequent 68.7 million GBP cost increase up to 151.8 million GBP were many and complex, but critical factors were: failure to freeze the design and significant subsequent design changes; changes in statutory requirements and building regulations; a new liability for VAT; inflation; delays to the building works; a large number of disputes and claims associated with construction works; changes to the design team’s fee rates; and the insolvency of works package contractors. | [2] |
| Colchester Regional Hospital Replacement, Nova Scotia | Canada | Original budget: 104 million CAD Revised cost: 184 million CAD | The original budget should have been considered to be preliminary, as it was based on limited information. Ineffective budgeting practices contributed to increases in costs. Supporting documentation prepared by the Department of Health and Wellness for the Cabinet for the first budget and two subsequent budget approvals was incomplete and contained inaccuracies, hindering effective decision-making. | [3] |
| Rocky Mountain Regional VA Medical Center located in Aurora, Colorado | US | Original budget: 328 million USD Revised cost: 1.73 billion USD Construction commenced in 2009 but excavating did not start until January 2012. Once it began, a new revised date for the project of 2015 was put forward. Then, in 2013, the contractor was unable to provide a workable plan to the budget. Expected completion date: 2013 Actual completion: July 2018 | Mismanagement: Veteran Affairs’ poor management of the project. Veteran Affairs was stripped of responsibility due to the House of Representatives’ misinformation on cost increases. Responsibility to complete the project was then given to the Army Corps of Engineers. Design flaws/changes occurred and the scope was changed. | [4–7] |
| William Beaumont Army Hospital Medical Center, El Paso, Texas | US | Original budget: 740.4 million USD Revised cost: 1.4 billion USD Construction commenced: 19 August 2013 Expected completion: 26 November 2016 Actual completion: 15 November 2019 | Design errors, changes in scope and contract changes occurred. A Defense Department audit found a total of 978 contract change requests and 453 engineering requests, including design errors and omissions. | [8] |
| The new Te Nikau, Grey Hospital and Health Center in Greymouth, | New Zealand | Original budget: 68 million NZD Revised cost: 121.9 billion NZD Construction commenced: May 2016 Expected completion: April 2018 Actual completion: July 2020 | The extra costs of completion was due to the rebuild at Canterbury (i.e., labor and materials). Contractual disputes of 31 million NZD occurred due to workers being unavailable and complex scope changes. Mold was found before the building was watertight, and all affected areas had to be replaced. Cladding had to be replaced due to storm damage. | [9,10] |
| Gold Coast University Hospital, Gold Coast | Australia | Original budget: 1.230 billion AUD Final business case: 1.549 billion AUD Revised cost: 1.76 billion AUD Construction commenced: December 2008 Expected completion: December 2012 Actual completion: July 2021 | At the time the budget was formulated, the project scope had not been fully developed. Moreover, no robust investment planning and analysis had been undertaken to determine the scope based on the likely outturn cost when the commitment was made. As a result, 2006 was deemed to be underestimated. The business case was based on a single solution. No benefits management framework was undertaken. Project announced in 2006. | [11] |
| Sunshine Coast Public University Hospital, Birtinya | Australia | Original budget: 940 million AUD Final business case: 1.93 billion AUD Revised cost: 1.87 billion AUD Construction commenced: October 2012 Expected completion: Spring 2016 Actual completion: April 2017 | The decision-to-build was made before the preliminary evaluation of options and before the business case was developed. The business case was based on a single solution. The original estimate was undertaken in 2006. A 2-year delay resulted in the health authority changing the project’s scope and providing additional services. It was delivered using a PPP. Construction was delayed in 2009 so the PPP market could recover from the global financial crisis. The original estimate did not include escalation costs. No benefits management framework was undertaken. Project announced in 2006, and it was initially expected to open in 2014. This delay resulted in a bed shortage. | [11] |
| Lady Cilento Children’s Hospital (now Queensland Children’s Hospital), South Brisbane | Australia | Original budget: 770 million AUD Final business case: 1.40 billion AUD Revised cost: 1.44 billion AUD Construction commenced: July 2010 Expected completion: January 2013 Actual completion: September 2014 | The decision-to-build was made before a preliminary evaluation of options and before the business case was developed. No alternative options were considered. The business case provided a definition of benefits, but they were not defined. Thus, there was no baseline to support their measurement. Project announced in 2006. | [11] |

Table S2

Context and meaning for hospital projects

| Hospital | Context | Meaning | Data sources |
| --- | --- | --- | --- |
| Fiona Stanley Hospital (No BIM) | Background: In 2004, the incumbent State Government of Western Australia (WA) announced that the FSH would be constructed in response to the Reid Report [17] into Health Reform. The FSH is a 783-bed modern tertiary health campus for public patients (16 operating theaters, 6300 rooms, and 3600 car bays). At the time of its completion, it was the most technologically sophisticated hospital and the State’s biggest building infrastructure project. Between 2004 and 2007, the capital budget increased from 420 million to 1.76 billion AUD. However, the Murphy Report [14] concluded that the original cost estimate was unrealistic, as it was based on a minimal understanding of the hospital’s services. The project also could not meet the original construction time identified in the business case and was between 3 and 4 ½ years later than initially planned. Information gaps were found to exist in the business case, which took 8 months to rectify. In addition, delays with approvals and inaccurate information hampered progress. Delivery: A two-stage managing contractor was based on a Guaranteed Maximum Price (GMP) with a shared savings regime between the managing contractor and the State. Stage 1 was equivalent to early contractor involvement (ECI). The use of ECI fostered a collaborative working environment, where the managing contractor and the State effectively combined to establish “one team” to develop the best project design solutions. A transparent and open-book approach enabled the State to be fully informed of the cost plan, program, and design development on a progressive basis through to the end of Stage 1, by which time a minimum of 80% of the trade packages was to be designed, tendered, and submitted for approval. Once the Stage 2 contract was awarded, the managing contractor assumed full responsibility for the design and delivery of the hospital, including commissioning and readiness for services. The facility management services contract combined elements of a PPP (e.g., long contract life and transfer of risk to the private sectors) with traditional modes of outsourced delivery. A contract for 4.3 billion AUD was signed 1 April 2014. Governance: The governance structure reflected the different roles of WA Health and the Department of Treasury and Finance (DTF). The Director-General of WA and the Treasury were accountable for ensuring that the hospital opened on time and on budget. The DTF-SP (Strategic Projects) was responsible for the construction. WA Health owns and operates the hospital. WA Health was responsible for making sure the hospital’s brief correctly reflected its service delivery requirements. The DTF-SP, acting on behalf of the Minister for Works, was accountable for delivering buildings that met WA Health’s needs. Between 2006 and 2010, a multi-agency FSH Steering Committee provided oversight of the project, including endorsing recommendations for the Expenditure Review Committee. In 2010, a Project Control Group was established to deal with operational matters. Scope change: Significant scope and design changes increased the size and estimated cost of the hospital a year into the design, with 255 million AUD State rehabilitation (140 beds added to the project). In addition, during the delivery phase, neonatal/obstetrics services, a new heart/lung transplant operating theater, and expansion of the ED were introduced. Up to 30 million AUD worth of additional works were incorporated but were delivered within the original budget. Quality: No significant issues with quality were identified during construction. During construction, the managing contractor: • Deployed a new digital pen, web-based defect management system, PenMatrix, to record and issue project defects; • Utilized a cloud-based operations and maintenance manual system, ZuTec, to create a digital handover manual; • Developed a detailed custom quality assurance operating system for the unique components of the project. The managing contractor conducted four separate inspections and re-inspections (pre-commissioning, post-commissioning, final inspection, and compliance checking) with the State, consultants, and the independent certifier to ensure that all quality issues were addressed immediately and continuous improvement was achieved. | Original budget: 420 million AUD Expected cost: 1.76 billion AUD Actual cost: 2.01 billion AUD The facilities management of nonclinical services (e.g., administration, cleaning, catering and building maintenance, furnishings, and selected medical equipment) was estimated to cost 2.5 billion AUD over 20 years. Expected completion: 23 December 2013. The contract was awarded to the managing contractor (MC) in February 2009, and construction commenced in September 2009. Site preparation commenced in July 2008. Actual completion: 6 December 2013, 17 days ahead of time. In addition, there were no contractual letters of dispute, no extension of time claims, and industry-leading safety culture. The project was opened in stages between October 2014 and March 2015. The lost time injury frequency rate (LTIFR) achieved at the completion of the project was 4.9, which is below the industry standard of 13.7. Other key performance issues included: • Zero contractual letters of dispute; • Zero extension of time claims; • 30 million AUD of additional works incorporated within the original budget. Disputes Facility Management Services Contract Lengthy contractual disputes impacted the costs of the contract. Issues with contract interpretation resulted in cost implications of approximately 10.4 million AUD in financial claims. Due to the delay in the opening of the hospital, costs to the facility management services contractor were incurred by the Department of Health: • 52.7 million AUD payment due to the delay in the opening of the hospital. These costs are included in the 125 million AUD allocated to the transition/delay-phased period costs below. • 1.82 million AUD, plus ongoing salary costs to engage an additional 170 Assistants-in-Nursing to bridge the gap between traditional orderly and porter services, as scoped under the contract. These costs are not payments under the contract but arose as a result of a lack of clarity about the scope of porter services provided by the contractor. After 2 years of operation in 2015/2016 and 2016/2017, facilities management and support services cost 331 million AUD, approximately 24.6 million AUD more than initial base estimates approved in 2011. Initial estimates did not include the final prices for four services, separate one-off payments for estates, and information and communications technology (ICT) and contract variations Benefit shortfalls: The facility management services were outsourced. This approach was a first for the WA government. Also, a detailed business case was not undertaken, and the information needs and requirements to operate the hospital were not considered during the business case and design. There was a shortage of beds, as population growth had not been given due consideration and being based on 2011 forecasts. Information and communication systems were unreliable and unstable. The quality of patient care was compromised as technology regularly malfunctioned, and information was not accessible for decision-making. Doctors could not access electronic records. The contractor for the facilities management had not provided a quality service for the sterilization of equipment. There was no effective asset management system to ensure that the hospitals had the right medical equipment in the right place at the right time. | [12–17] |
| Perth Children’s Hospital (BIM) | Background: This dedicated children’s hospital was constructed to replace the Princess Margaret Hospital (PMH) in Perth, Western Australia. In 2004, the Health Reform Committee recommended replacing the PMH as the State’s dedicated pediatric hospital. On 25 November 2010, the incumbent government approved a 1.17 billion AUD business case for PCH. The hospital covers 125 000 m2 across six treatment floors, two research floors, and two basement floors. A helipad is also included on the roof. Delivery: Three companies were shortlisted for the project in April 2011. The State government knowingly accepted a competitive bid with little room for error from the managing contractor (MC). The State government had not previously used the MC to manage projects of such scale and complexity. Concerns on utilizing an organization whose extensive experience focused on civil projects and on choosing the lowest price were raised by the Construction, Forestry, Mining, and Energy Union (CFMEU). Stage 1 design development and external subcontract pricing were undertaken in parallel with early site works that were completed in December 2012. The project was procured using a two-stage MC who guaranteed a fixed price for Stage 2. The process to assess the MC for the Stage 2 offer was robust, and the decision to accept the offer was reasonable. The assessment was based on the managing contractor’s cost plan and construction program. The State’s processes to review the concept, schematic, and detailed designs were robust and provided the Department of Health and end-users with sufficient opportunity to provide input. Thus, the managing contractor was responsible for the design and construction, which accounted for 80% of the contract (Stage 2). Therefore, 20% of the value of work had not been fully designed. This type of contract was put in place to manage (mitigate) the State government’s risk exposure and cost escalation. The contract was “State-friendly” and thus provided reasonable levers to obtain contractual compliance. The managing contractor did not fully understand the construction program status during the project delivery phase and did not perform the analysis required to forecast a realistic date for practical completion. Governance: A governance structure was established to oversee the managing contractor proactively. However, it added complexity due to its dual governance/dual accountability, as the Department of Treasury was responsible for the construction while the Department of Health managed all aspects of commissioning. Confusion over roles and responsibilities resulted in no agreed-upon overview design and implementation plan for information and communication technology until June 2015, even though 245 million AUD was approved in November 2013 in the business case. As a result, the Department of Health did not know how the project’s cost was tracking. Ministers were provided with information in a piecemeal manner, and attribution of accountability was difficult, given the dual governance system. An Integrated Program Management Office was established but did not effectively collaborate with the DFT-SP. A combative and siloed mentality prevailed, rather than collaborative relations. The managing contractor had difficulty managing its subcontractors during the construction process. Issues associated with non-payment and liquidations arose. The problems with subcontractors were under-reported to the PCH Taskforce. The managing contractor had an adversarial relationship with its subcontractors, contributing to communication issues and poor morale on site. There was a fear that, if safety issues were reported, bullying would occur. There was a high turnover of staff within the managing contractor’s team. Scope changes: While the hospital was under construction, the State changed the project’s scope by adding a 24-bed surgical short stay, adding 37.1 million AUD. The Australian Medical Association (AMA) requested another floor, but the health minister refused to approve the extra funding required. By not adding the extra floor, the AMA stated that the government had lost the opportunity to “future-proof” the hospital. Quality: During construction, significant noncompliance issues emerged. The major problems were asbestos in unitized roof panels, a curtain wall, and an atrium ceiling, which partly collapsed during a storm. Lead was also found to contaminate the water, and there was stainless steel pipe corrosion, burst rubber expansion joints, and fire safety issues. Reports revealed that there was lax reporting of quality issues, poor quality control, and defects. Building materials were often sourced through multiple layers of subcontracting with complex, international supply chains. In addition, an overreliance on third-party certification increased the risk of nonconforming products being installed. | Expected cost: 1.2 billion AUD Actual cost: Yet to be finalized. The MC issued a writ with the WA Supreme Court seeking 300 million AUD. Expected completion: On 1 July 2011, the MC announced that it was due to complete construction by 30 June 2015. Actual completion: Accepted practical completion on 20 April 2017, with water contamination listed as a minor defect. Lead was found in the water and further delayed the project to May 2018 (almost a 3-year delay). Delays were estimated to cost taxpayers 100 million AUD, including a 15 million AUD loss in revenue from an onsite car park. The delay also meant that the existing PMH had to receive additional funding. provide services. Benefit shortfall: An opportunity to add two additional floors was rejected despite requests from the AMA and stakeholders. The estimated cost would have been 70 million AUD. By the time the project was completed, signs showed that there were not enough beds. | [13,18–25] |
| New Royal Adelaide Hospital (BIM) | Background: One of Australia’s most advanced hospitals, providing a full range of complex clinical care. The facility provides 800 beds, standardized inpatient rooms, 40 technical suites, and leading technology. The hospital is the largest social infrastructure built in Australia. The nominal budget was approximately 2.4 billion AUD. The estimated costs for design and construction were 1.85 billion AUD by South Australia (SA) Health Partnership Pty. Ltd. (i.e., Project Co) and State-funded works of 591.5 AUD. The hospital was delivered using a serviced infrastructure model. A project agreement between the State of SA and Project Co, executed in May 2011, provided the rights and obligations of the parties from design to construction and provided a range of facility management ICT support services. Delivery: Procured using a PPP arrangement operating under a project agreement between the State and Project Co (known as Celsus) over 35 years (ending in June 2046), covering the design, construction, and operating phases. The budget in 2015 was 2.3 billion AUD. Project Co failed to achieve the revised practical completion date due to a major default failure to adopt best construction practices. Not all State operational commissioning activities were fully complete and functional at the facility at commercial acceptance. Not all items were included in the list of commercial acceptance; outstanding items were completed and closed out as of 2 November 2017. The first quarterly service payment was not reduced to reflect the time when the RAH was not operational. Project Co was not required to provide the full suite of facility management services during the first quarter. While the project agreement allowed the quarterly service payment to be adjusted to reflect the volume of catering services provided, it did not permit the payment to be discounted for other services not provided by Project Co during the quarter, due to the hospital not being operational. Governance: SA Health implemented a governance structure to overlook the project. The arrangements changed as the project progressed and in order to respond to ongoing commissioned independent consultant reviews. The reviews had raised concerns. For example, in June 2013, a review identified the need to strengthen and refocus the governance framework, develop a refreshed business case, and engage additional resources, including change management, operations and commissioning, and assurance management. Then, in 2014, actions were taken to engage a PPP relationship and clinical services (e.g., identify models of care). A functional review was undertaken in 2015 to examine program structures, progressing workstreams, status, and actions taken to improve clinical engagement. Also, the Operations Boards, roles, and interfaces of senior resources and the like were reviewed. After the reviews, in 2015, the business case had not been updated, and there was no formal process to monitor the project’s progress. Quality: The State raised concerns that Project Co did not report all quality failures. It requested Project Co to provide details of its process to identify and report on quality failures. Material defects were deemed to impact safety, clinical care, and long-term operating costs. Five defects were referred to operation to determine the compensation payable to the State. Examples of defects included: • Level 1 western plant primary water pump failure; • Level 4 technical suites—nonconforming works; • Technical compliance testing. Several items were not completed at commercial acceptance; there were minor defects (snags), minor physical works, testing, and commissioning. Disputes about whether specific works constituted modifications or defects prevailed. For example, the State issued modification orders for certain works, which needed to be performed urgently, but expressly reserved its right to recover the costs of those works from Project Co. In these instances, the State considered that the work (or part of the works) included in these modification orders required rectification and therefore was a defect. Under the project agreement, Project Co was liable for the cost of defect rectification works. | Expected cost: 2.3 billion AUD Construction budget: 1.849 billion AUD State-funded works: 417.74 AUD Actual cost: 2.44 billion AUD Original expected practical completion: 18 January 2016 Under the project agreement and deed of settlement and release, the Minister of Health agreed to extend the practical completion by 76 days to 4 April 2016. Original expected commercial acceptance: 3 July 2016 The project experienced a delay of 345 days in achieving technical and commercial acceptance. The delay created cost pressure that included running the program office, procurement holding costs, and contractors’ continued engagement. As a result, in December 2016, the State government approved 51.24 million AUD in additional funding to accommodate the delays and realign the project’s delivery dates: Revised expected practical completion: 15 January 2017 Practical completion was not achieved until 17 March 2017, which impacted the revised commercial acceptance date that assumed patients would move in July 2017. Revised expected commercial acceptance: 15 April 2017 In May 2017, the SA Government announced that the move to the new hospital would take place on 5 September 2017 instead. Dual running costs of existing and new hospitals were incurred, and an additional 11.8 million AUD was made available Actual practical completion: 15 March 2017 Actual commercial acceptance: 13 June 2017 Benefit shortfalls: The hospital is considered not to be fit for the purpose and too small. | [26–29] |

References

[1]	Greenwood DJ, Osborne AN, Aggiag MA. A comparative analysis of administrative delays in hospital buildings. In: Akintoye A, editor. Proceedings of the 17th Annual ARCOM Conference; 2001 Sep 5–7; Salford, UK. Reading: Association of Researchers in Construction Management; 2001. p.795–802.

[2]	National Audit Office. Cost over-runs, funding problems and delays on Guy’s Hospital phase III development. London: Comptroller and Auditor General, Department of Health; 1998 May 29 [2021 Apr 19]. Available at: https://www.nao.org.uk/pubsarchive/wp-content/uploads/sites/14/2018/11/Department-of-Health-Cost-Over-runs-Funding-Problems-and-Delays-on-Guys-Hospital-Phase-III-Development.pdf.

[3]	Office of the Auditor General of Nova Scotia. Health and wellness: Colchester Regional Hospital replacement [Internet]. Office of the Auditor General of Nova Scotia; 2011 May [2021 Apr 19]. Available from: https://oag-ns.ca/sites/default/files/publications/2011 – May – Ch 04 – DHW – Colchester Regional Hospital Replacement.pdf.

[4]	Department of Veteran Affairs. Review of the replacement of the Denver Medical Centre, Eastern Colorado health care systems. Department of Veteran Affairs; 2016 Sep 21 [2021 Apr 19]. Available from: https://www.va.gov/oig/pubs/vaoig-15-03706-330.pdf.

[5]	GAO. VA construction: additional actions needed to decrease delays and lower costs of major medical-facility projects. A report to the chairman, committee on veterans’ affairs, house of representatives [Internet]. GAO; 2013 Apr [2021 Apr 19]. Available from: https://www.gao.gov/assets/gao-13-302.pdf.

[6]	Holdman R. Timeline of events and delays: new VA hospital in Aurora, Colorado [Internet]. CBS Broadcasting Inc.; 2018 Feb 15 [2021 Apr 19]. Available from: https://denver.cbslocal.com/guide/timeline-va-hospital-aurora/.

[7]	Olsen K. Never again [Internet]. The American Legion; 2018 Sep 20 [2021 Apr 19]. Available from: https://www.legion.org/magazine/243186/never-again.

[8]	Paavola A. How an army hospital project in Texas went $629m over budget [Internet]. Becker’s Hospital Review E-Weekly; 2019 Oct 18 [2021 Oct 19]. Available from: https://www.beckershospitalreview.com/capital/how-an-army-hospital-project-in-texas-went-629m-over-budget.html?oly_enc_id=3747B9812012C6X.

[9]	Young V. Fletcher in a $31m dispute with the ministry over Greymouth hospital [Internet]. NZ Herald; 2019 Oct 15 [2020 Apr 21]., Available from: https://www.nzherald.co.nz/business/fletcher-in-31m-dispute-with-ministry-over-greymouth-hospital/SIVMTFVR4RKJWSSWKICVE54CA4/, Accessed 21st April 2020

[10]	Carroll J. Grey hospital to open two years overdue and $54m overbudget [Internet]. Stuff; 2020 Jun 25 [2021 Apr 22]. Available from: https://www.stuff.co.nz/national/health/121941149/grey-hospital-to-open-two-years-overdue-and-54m-overbudget.

[11	QAO. Hospital infrastructure projects [Internet]. Brisbane: Queensland Audit Office; 2014 [2021 Apr 21]. Available from: https://www.qao.qld.gov.au/sites/default/files/reports/rtp_hospital_infrastructure_projects.pdf.

[12]	Education and Health Standing Committee. Managing the transition? The report of the inquiry into the transition and operation of services at Fiona Stanley Hospital [Internet]. Education and Health Standing Committee; 2015 [2021 Jul 17]. Available from: https://www.parliament.wa.gov.au/parliament/commit.nsf/(Report+Lookup+by+Com+ID)/70864F6AC389DCFA48257F08002B75F9/$file/151120+Final+Version+post-adoption+Signature+PDF+Cropped.pdf.

[13]	Langoulant J. Special inquiry into government programs and projects: final report [Internet]. Government of Western Australia; 2018 Feb [2021 May 22]. Available from: https://apo.org.au/sites/default/files/resource-files/2018-02/apo-nid135381_11.pdf.

[14]	Murphy C. Fiona Stanley Hospital project [Internet]. Perth: Western Australia; 2010 Jun 23 [2021 May 22]. Available from: https://www.parliament.wa.gov.au/publications/tabledpapers.nsf/displaypaper/3812240a68c5ce14f5daf6934825774b0017c88e/$file/2240+-+oag+-+fiona+stanley.pdf.

[15]	O’Connor A. Serco’s Fiona Stanley Hospital sterilization contract was terminated after failures [Internet]. ABC News; 2015 Apr 20 [2021 Jul 16]. Available from: https://www.abc.net.au/news/2015-04-20/serco-hospital-sterilisation-contract-cancelled/6406106.

[16]	O’Connor A. AMA delivers devastating critique of Fiona Stanley Hospital in Perth [Internet]. ABC News; 2015 Aug 15 [2021 Jul 17]. Available from: https://www.abc.net.au/news/2015-08-19/ama-delivers-devastating-critique-of-fiona-stanley-hospital/6708650.

[17]	Reid M. A healthy future for Western Australia. A report of the Health Reform Committee [Internet]. Perth: Western Australian Health Department; 2004 [2021 May 22]. Available from: https://ww2.health.wa.gov.au/~/media/Files/Corporate/Reports%20and%20publications/PDF/Report_of_the_Health_Reform_Committee.ashx.

[18]	CFMEU. Management and oversight of the Perth Children’s Hospital Project. A submission from the Construction, Forestry, Mining and Energy Union (CFMEU) to the Western Australia Legislative Assembly Public Accounts Committee Inquiry [Internet]. CFMEU; 2017 Aug 14 [2021 May 21]. Available from: https://parliament.wa.gov.au/Parliament/commit.nsf/luInquiryPublicSubmissions/F1FCF02833C67007482581A0000CCAA5/$file/20170814%20-%20Submission%20015%20-%20CFMEU%20Redacted.pdf.

[19]	Emmerson D. Building delays hit children’s hospital [Internet]. The West Australian; 2015 Oct 6 [2021 Jun 28]. Available from: https://thewest.com.au/news/wa/building-delays-hit-childrens-hospital-ng-ya-130090.

[20]	Government of Western Australia. Perth Children’s Hospital. Building commission audit report, Department of Commerce, Perth [Internet]. Government of Western Australia; 2017 April [2021 May 21]. Available from: https://www.commerce.wa.gov.au/sites/default/files/atoms/files/final_report_-_perth_childrens_hospital_audit.pdf.

[21]	Kagi J. Perth Children’s Hospital builder John Holland launches $300 million legal action against WA government [Internet]. ABC News; 2019 Nov 27 [2021 May 21]. Available from: https://www.abc.net.au/news/2019-11-27/perth-childrens-hospital-builder-john-holland-launches-legal-bid/11741512.

[22]	Khorshid O. Australian Medical Association (WA) submission—inquiry into the management and oversight of the Perth Children’s Hospital project [Internet]. Australian Medical Association; 2017 [2021 May 21]. Available from: https://parliament.wa.gov.au/Parliament/commit.nsf/luInquiryPublicSubmissions/1468285BE7D06D52482581A3001521D3/$file/20170807%20-%20Submission%20014%20-%20AMA%20(WA)%20REDACTED.pdf.

[23]	Mercer D. State sparred panel fix bill at Perth Children’s Hospital [Internet]. The West Australian; 2016 Jun 1 [2021 Jun 28]. Available from: https://thewest.com.au/news/wa/state-spared-panel-fix-bill-at-perth-childrens-hospital-ng-ya-108595.

[24]	Parker G. The detail hospital contractor John Holland didn’t want you to see [Internet]. The West Australian; 2017 Jan 10 [2021 May 20]. Available from: https://thewest.com.au/ news/wa/the-detail-hospital-contractor-john-holland-I-want-you-to-see-ng-b88347847z.

[25]	Public Accounts Committee. (2018). PCH—a long awaiting period [Internet]. Perth: Parliament of Western Australia; 2018 Mar 22 [2021 Nov 15]. Available from: https://www.parliament.wa.gov.au/parliament/commit.nsf/(Report+Lookup+by+Com+ID)/A5D4EC94C80CBC3048258258000A42FB/$file/60282652.pdf.

[26]	Auditor General. New Royal Adelaide Hospital. Government of South Australia, report of the Auditor-General, supplementary report for the year ended 30 June 2017 [Internet]. Adelaide: Auditor-General’s Department; [2021 Jun 21]. Available from: www.audit.sa.gov.au.

[27]	Keane D. Royal Adelaide Hospital cost saga continues with potential rebuild of emergency rooms [Internet]. ABC News; 2018 Mar 25 [2021 Jun 24]. Available from: https://constructionadvisor.com.au/royal-adelaide-hospital-cost-saga-continues-with-potential-rebuild-of-emergency-rooms/.

[28]	McLennan L, Donnellan A. New Royal Adelaide Hospital completion deadline now officially missed [Internet]. ABC News; 2016 Apr 5 [2021 Jul 20]. Available from: https://www.abc.net.au/news/2016-04-05/default-notice-against-rah-completion-deadline/7298578.

[29]	Scopelianos S. Timeline: new Royal Adelaide Hospital plagued with issues from the start [Internet]. ABC News; 2017 May 8 [2021 Jun 24]. Available from: https://www.abc.net.au/news/2017-01-24/new-royal-adelaide-hospital-plagued-with-issues-from-start/8204004?nw=0.